## Triggers
Step | Details of the step (milestones) | Responsibility | Status | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
1. Risk Analysis | 1.1. Hazard selection - specifics | TWG
| 1.2. Historical impacts analysis | DP Team
| 1.3. Prioritisation of impacts to focus on, based on impact analysis | TWG
| 1.4. Agree on the vulnerability and exposure indicators that will be used in the trigger model, based on the prioirtized impacts | TWG
| 1.5. Exposure analysis | DP Team
| 1.6. Vulnerability analysis | DP Team
| 1.7. Results for the risk analysis are presented to the TWG and relevant actors for recommendations and endorsement | TWG
2. Menu of forecasts | 2.1. Develop the menu of forecasts | FbF Team
| 2.2. Decide on forecasts to use - trigger forecast | TWG
| 2.3. Forecask skill analysis | FbF Team with KMD, ForPAc, ICPAC, RCCC, International Climate Science Institutions
| 2.4. Decide on forecast thresholds to use as triggers for action (amounts, probability, skill and lead times), linked to 6.1 under Early Actions | TWG
| 2.5. Discuss and develop the Stop mechanism for early action | TWG
3. Define hazard magnitudes | 3.1. Compute hazard magnitudes (return periods) | DP Team
4. Analyse links between hazard magnitude and impact | 4.1. Develop impact hazard catalog | DP Team
| 4.2. Decide on methodology for developing the hazard – impact curves (Expert knowledge / the composite index, Elementary modelling, Statistical modelling) | TWG
| 4.3. Develop hazard – impact curves | DP Team
| 4.4. Agree on point(s) of hazard - impact curve to take action on, considering different hazard magnitudes and levels of impact, linked to 6.1 under Early Actions | TWG
| 4.5. Develop forecast trigger options, based on 2.4 and 4.3 above | FbF Team, DP Team
5. Generate impact-based forecast intervention map | 5.1. Decide how best to put together the impact-based forecast (modelling, combine layers, qualitative statements etc) | TWG
| 5.2. Develop impact-based forecasts (trigger model) | DP Team, FbF Team
| 5.3. Desk simulations are conducted to test the impact-based forecast (trigger model) | DP Team, FbF Team
| 5.4. Review and agree on impact-based forecast (trigger model) developed | TWG
| 5.5. The TWG presents the trigger model to relevant actors - feedback is incorporated if needed | TWG
| 5.6. The impact-based forecast (trigger model) is diseminated to KRCS, relevant national stakeholders/ institutions | TWG

## Early actions
Step | Details of the step (milestones) | Responsibility | Status | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
1. Identify climate related risks | 1.1. Risk analysis as developed under the trigger methodology is used here | DP Team with TWG
2. Conduct research and review of documentation | 2.1. Desk review and key informant interviews to identify where there might be pre-existing work/ actions to build on | FbF Team
| 2.2. Develop a repository of actions that have been successfully used for the same risk (as in 1.1. above) in Kenya | FbF Team
| 2.3. Conduct study SWOT analysis (of strengths, weakness, opportunities, and threats) to identify effectiveness, impact, gaps of implementation and possibilities of improvement of actions that already exist | FbF Team
| 2.4. SWOT analysis specific to CTP as an early action | CTP Team
| 2.5. Develop potential actions report | FbF Team, CTP Team
3. Brainstorm possible forecast based early actions | 3.1. Based on the potential actions report in step 2, identify what actions might be appropriate to take based on a forecast. Include new actions not already being implemented. Consider two categories of actions: i) Early Actions (mitigation/ prevention); ii) Preparedness for Response actions | TWG
| 3.2. Conduct study on feasibility of actions identified in 3.1., considering creteria: Consistency with Government and/or other Institutional Plans/Policies, Prevention/Mitigation of Impact and preparedness for response, Scale, Practicality, Social acceptability, Value for Money, Relevance, Appropriate financing options, Efficiency | FbF Team
| 3.3. Develop early actions feasibility study report and present a summary to the TWG | FbF Team
4. Prioritize early actions | 4.1. Prioritise a set of early actions to be implemented, based on the feasibility study report. Consider: Time and Duration of action, Capacity to Implement, Resources required, Access considerations. Include prioritisation of CTP | TWG
| 4.2. Develop a short list of priority early actions | TWG
| 4.3. Identify capacity enhancement needs to enable implementation of early actions, and plan for capacity support | FbF Team
5. Elaborate list of high-priority early actions | 5.1. Develop a Theory of Change for each early action on the short list | TWG
| 5.2. Identify target level of implementation, coverage and sector for the respective actions | TWG
| 5.3. Conduct Cost Benefit Analysis of each early action and develop a report and summary for presentation to the TWG | FbF Team
| 5.4. Discussion and agreement on actions to take forward based on the Cost Benefit Analysis | TWG
| 5.5. For the agreed actions, identify the time it will take to prepare and implement the actions and identify approximately for how long the actions will last | TWG
| 5.6. Identify implications of ‘Acting in vain’, and ‘no-regret actions’/ 'low-regret actions' | TWG
6. Match actions with forecast trigger options | 6.1. Specify which forecast triggers will be used for each of the actions, linked to 2.4, 4.4 and 4.5 under Triggers | TWG, with KMD
| 6.2. Early Actions and triggers are agreed by TGW | TWG
| 6.3. TWG agrees on tasks, roles, responsibilities and capacities for taking early actions | TWG

## EAP development
EAP section | EAP sub-section | Responsibility | Status | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
1. Executive summary | Summary | PM
2. Key actors | Actors | PM
3. Risk Assessment | 3.1. Hazard Selection | FbF Team
| 3.2. Exposed elements and their vulnerability factors | DP Team
| 3.3. Prioritized Impact | FbF Team
4. Trigger Model (Impact based Forecast model) | 4.1 Trigger Statement | FbF Team
| 4.2. Forecast selection | DP Team
| 4.3. Definition and justification of the Impact Level | DP/ FbF Team
| 4.4. Identification of the intervention area | DP/ FbF Team
5. Selection of Actions | 5.1. Early Action Selection Process | FbF Team
| 5.1.1 Theory of change | FbF Team
5.2 Evidence Base - that the selected actions will reduce disaster impacts
| 5.3. IFRC Planned operations (Operational matrix) | FbF Team
| 5.4. Usefulness of actions in case of non-occurring event (Acting in vain) | FbF Team
5.5. Feasibility
6. EAP activation process | 6.1 Early Action Implementation process
6.2 Trigger activation system
6.3 Selection of target population
6.4 Stop Mechanism
7. Monitoring, Evaluation, Accountability and Learning | 7.1. Monitoring the EAP implementation | MEAL Team
| 7.2. Trigger Evaluation | DP/ FbF Team
| 7.3. Evaluation of impact of early actions after activation | MEAL Team
| 7.4. Identification and Documentation of Lessons Learned | MEAL Team
8. National Society Early Action Capacity | 8.1. Operational, thematic and administrative capacity | FbF Team
| 8.2. Strategies and plans | PM
| 8.3. Financial capacity to advance funds | PM
9. Finance and Logistics | 9.1. Budget | Finance Team
| 9.2. Readiness cost | Finance Team
| 9.3. Prepositioning | Finance Team
| 9.4. Early action cost | FbF/ Finance Team
10. EAP endorsement | 10.1. Endorsement by National Society | PM
| 10.2. Endorsement by Government and other key stakeholders | PM
11. Conclusion |  | PM

## EAP validation
EAP validation action | Responsibility | Status | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01
1. EAP is approved by the TWG | PM
2. EAP is endorsed by KRCS senior management | PM
3. EAP is endorsed by Goverment officials and key stakeholders | PM
4. EAP is approved by the IFRC validation committee | PM