FILLED TEMPLATE Chronological activation process – actions and responsible personnel

| - days before the event occurs |  |
| --- | --- |
| NS Director General | - To conduct an emergency briefing for all respective NATIONAL SOCIETY department managers - To report to IFRC Geneva on the activation - To validate the Early Action activation costs for the lead time, based on calculations provided by NATIONAL SOCIETY FbF Focal Point - To ensure availability of Funds |
| NATIONAL SOCIETY Head of DM department | - To disseminate information on approaching hazard to NATIONAL SOCIETY branch Director(s) - To communicate with NATIONAL SOCIETY branch Director(s) to activate NDRT, FbF staff/volunteers - To disseminate a letter of alert to relevant partners (DRCU, PNs) - To coordinate communication with the province, where the forecast of the extreme event was activated - To mobilize the equipment and other means that will facilitate the distribution process (HQ level) |
| NATIONAL SOCIETY FbF team and EAP Focal Point | - To identify the districts for intervention and communication, based on the procedures described in paragraph 4.6 – Intervention map - To follow up on the Protocol - To make the necessary corrections into the activation costs for four days (the lead time) based on the number of affected communities (HH) - To notify NATIONAL SOCIETY logistic manager on the EAP activation for the planning of further logistics - To share the overall distribution plan with NATIONAL SOCIETY Branch director(s) |
| Logistic manager | - To activate the logistic protocol (mobilization of distribution items, transportation), recognition of delivery routes/locations in coordination with the FBF team and suppliers - To activate the logistics chain and prepare means of transportation of goods to identified locations - To activate the logistics chain in the field - To transport supplies to identified points - To ensure the security of supplies for shipment |
| NATIONAL SOCIETY Organizational department | - To follow up on Insurance activation for a team of volunteers |
| NATIONAL SOCIETY Provincial and District Director(s) | - To disseminate information on the phenomenon to NATIONAL SOCIETY NDRT, FbF staff/volunteers - Coordinate activities with local, district and provincial authorities - To request a beneficiary list from the local authorities of respected communities - To share the distribution plan with NATIONAL SOCIETY NDRT, FbF staff/volunteers - To inform about distribution points - To support teams on the ground through communication and coordination in the areas of intervention - To activate the FbF staff/volunteers to take preventive measures by conducting awareness campaigns in selected communities |
| - days before the occurrence of the event |  |
| NATIONAL SOCIETY Head of DM department | - To start the execution of the distribution plan or activate the Stop Mechanism in accordance with the updated information - To monitor the communication system - To support the systematization and registration of beneficiaries for the intervention |
| NATIONAL SOCIETY FbF and EAP Focal Point | - To move to the corresponding region to support the teams on the ground. - To ensure a proper mobilization of the equipment and means on the field level - To monitor the information on the weather forecast from hydromet to follow up the Stop Mechanism if necessary - To direct actions on the ground - To validate the press releases - Execute the distribution plan - To monitor the distribution - To validate the list of distribution reports - Report and update the Head of DM department |
| NATIONAL SOCIETY Provincial and District Director(s) | - To execute the distribution plan - To verify the beneficiary list during the distribution process - To distribute items selected for interventions - To collaborate with representatives of local authorities at all times |
| Logistic manager | - To activate the logistics chain in the field - To transport supplies to identified points - To ensure the security of supplies for shipment |
| - days and 1 day before the occurrence of the event |  |
| NATIONAL SOCIETY Head of DM department | - To monitor the EAP activation and the distribution process from HQ via e-mail, phone, WhatsApp etc. |
| NATIONAL SOCIETY FbF and EAP Focal Point | - To direct actions on the ground - To validate the press releases - Execute the distribution plan - To monitor the distribution - To validate the list of distribution reports - Report and update the Head of the DM department daily |
| NATIONAL SOCIETY Provincial and District Director(s) | - To continue the distribution - To verify the beneficiary list during the distribution process - To continue with awareness campaigns in communities - To collaborate with representatives of local authorities at all times |