Implementation process

Example: Mozambique Cyclone

| No. | Activity: | Responsibility: | Local: | Schedule: |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 72 hours / 3 days | 48 hours / 2 days | 24 hours / 1 day |
| Early Actions (after trigger) |  |  |  |  |  |  |
| 1.1 | Select focus districts based on 72-hours forecast information and community selection criteria established above | CVM and FbF Team | Maputo |  |  |  |
| 1.2 | Disseminate information on the phenomenon in question to relevant CLGRCs and CVM volunteers | INAM, DNGRH, INGC | All provinces |  |  |  |
| 1.3 | Activation of CLGRCs and relevant CVM volunteers to inform communities | INGC and CVM | Selected Communities |  |  |  |
| 1.4 | Demonstration of how to reinforce the houses | FbF Team and Provincial CVM Delegations | Selected Communities |  |  |  |
| 1.5 | Distribution of home reinforcement materials to educational communities and pamphlets | FbF Team and Provincial CVM Delegations | Selected Communities |  |  |  |
| 1.6 | Reinforcement of individual houses | Individuals, CVM Volunteers, CLGRC | Selected Communities |  |  |  |
| 1.7 | Demonstration of how to strengthen schools | FbF Team and Provincial CVM Delegations | Selected Communities |  |  |  |
| 1.8 | Reinforcement of schools | School Council, CVM Volunteers, CLGRC | Selected Communities |  |  |  |
| 1.9 | Distribution of construction material to school boards | FbF Team and Provincial CVM Delegations | Selected Communities |  |  |  |
| 1.10 | Demonstration of how to use chlorine/ Certeza and on individual hygiene | FbF team, volunteers and CLGRC | Selected Communities |  |  |  |
| 1.11 | Distribution of chlorine, buckets and educational pamphlets in communities | FbF team, volunteers and CLGRC | Selected Communities |  |  |  |
| 1.12 | 6 hours before the predicted landfall, call off the distribution activities in the communities and encourage volunteers and community members to seek shelter in secure places | FbF team, volunteers and CLGRC | Selected Communities |  |  |  |

Template

| No. | Activity: | Responsibility: | Local: | Schedule: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 72 hours / 3 days | 48 hours / 2 days | 24 hours / 1 day | after activation |
| Early Actions (after trigger) |  |  |  |  |  |  |  |
| 1.1 | e.g. Dissemination of warning messages/distribution of goods etc. | e.g. RCRC NS, FbF Team, volunteers etc. | e.g. specific community/region/all provinces etc. |  |  |  | e.g. PDM, reports, |
| 1.2 |  |  |  |  |  |  |  |
| 1.3 |  |  |  |  |  |  |  |
| 1.4 |  |  |  |  |  |  |  |
| 1.5 |  |  |  |  |  |  |  |
| 1.6 |  |  |  |  |  |  |  |
| 1.7 |  |  |  |  |  |  |  |
| 1.8 |  |  |  |  |  |  |  |
| 1.9 |  |  |  |  |  |  |  |
| 1.10 |  |  |  |  |  |  |  |
| 1.11 |  |  |  |  |  |  |  |
| 1.12 |  |  |  |  |  |  |  |